## Template Instructions
Implementation Plan - Template Instructions | CDBHI PROJECT IMPLEMENTATION PLAN | CDBHI PROJECT IMPLEMENTATION PLAN | CDBHI PROJECT IMPLEMENTATION PLAN | CDBHI PROJECT IMPLEMENTATION PLAN
Purpose |  | Use this template to describe the principal results the proposed project will accomplish, the major steps required, who will be responsible, when the work will occur, and how progress and results will be measured.
1. Purpose and Required Use | 1. Purpose and Required Use | 1. Purpose and Required Use | 1. Purpose and Required Use | 1. Purpose and Required Use
The implementation plan is a concise, results-oriented summary of how the applicant will carry out the proposed project. It should demonstrate that the proposed approach is feasible, appropriately sequenced, measurable, and consistent with the application narrative and budget. If selected for funding, the plan may be clarified or modified during subaward negotiations. The approved implementation plan will form part of the project’s performance framework and may be used to structure quarterly progress reporting, monitoring, technical assistance, and approved modifications. | The implementation plan is a concise, results-oriented summary of how the applicant will carry out the proposed project. It should demonstrate that the proposed approach is feasible, appropriately sequenced, measurable, and consistent with the application narrative and budget. If selected for funding, the plan may be clarified or modified during subaward negotiations. The approved implementation plan will form part of the project’s performance framework and may be used to structure quarterly progress reporting, monitoring, technical assistance, and approved modifications. | The implementation plan is a concise, results-oriented summary of how the applicant will carry out the proposed project. It should demonstrate that the proposed approach is feasible, appropriately sequenced, measurable, and consistent with the application narrative and budget. If selected for funding, the plan may be clarified or modified during subaward negotiations. The approved implementation plan will form part of the project’s performance framework and may be used to structure quarterly progress reporting, monitoring, technical assistance, and approved modifications. | The implementation plan is a concise, results-oriented summary of how the applicant will carry out the proposed project. It should demonstrate that the proposed approach is feasible, appropriately sequenced, measurable, and consistent with the application narrative and budget. If selected for funding, the plan may be clarified or modified during subaward negotiations. The approved implementation plan will form part of the project’s performance framework and may be used to structure quarterly progress reporting, monitoring, technical assistance, and approved modifications. | The implementation plan is a concise, results-oriented summary of how the applicant will carry out the proposed project. It should demonstrate that the proposed approach is feasible, appropriately sequenced, measurable, and consistent with the application narrative and budget. If selected for funding, the plan may be clarified or modified during subaward negotiations. The approved implementation plan will form part of the project’s performance framework and may be used to structure quarterly progress reporting, monitoring, technical assistance, and approved modifications.
Important |  | The implementation plan is not a weekly task list. Include the major activities and milestones necessary to accomplish meaningful project results; omit routine meetings, general administration, and minor operational steps unless they are essential to implementation.
2. Applicant Instructions | 2. Applicant Instructions | 2. Applicant Instructions | 2. Applicant Instructions | 2. Applicant Instructions
1 | Complete the project information on the cover page and provide an implementation plan covering the entire proposed project period. | Complete the project information on the cover page and provide an implementation plan covering the entire proposed project period. | Complete the project information on the cover page and provide an implementation plan covering the entire proposed project period. | Complete the project information on the cover page and provide an implementation plan covering the entire proposed project period.
2 | Include approximately three to six SMARTIE objectives. A different number may be used when reasonably necessary for the project’s scope, but objectives should not be fragmented into minor tasks. | Include approximately three to six SMART objectives. A different number may be used when reasonably necessary for the project’s scope, but objectives should not be fragmented into minor tasks. | Include approximately three to six SMART objectives. A different number may be used when reasonably necessary for the project’s scope, but objectives should not be fragmented into minor tasks. | Include approximately three to six SMART objectives. A different number may be used when reasonably necessary for the project’s scope, but objectives should not be fragmented into minor tasks.
3 | Use one objective form for each SMARTIE objective. Copy the blank form as needed. | Use one objective form for each SMART objective. Copy the blank form as needed. | Use one objective form for each SMART objective. Copy the blank form as needed. | Use one objective form for each SMART objective. Copy the blank form as needed.
4 | Include at least one objective addressing implementation or population reach and at least one objective addressing an intended short-term result or benefit. | Include at least one objective addressing implementation or population reach and at least one objective addressing an intended short-term result or benefit. | Include at least one objective addressing implementation or population reach and at least one objective addressing an intended short-term result or benefit. | Include at least one objective addressing implementation or population reach and at least one objective addressing an intended short-term result or benefit.
5 | Identify realistic targets that reflect the applicant’s proposed scope, requested budget, experience, staffing, service area, and population. | Identify realistic targets that reflect the applicant’s proposed scope, requested budget, experience, staffing, service area, and population. | Identify realistic targets that reflect the applicant’s proposed scope, requested budget, experience, staffing, service area, and population. | Identify realistic targets that reflect the applicant’s proposed scope, requested budget, experience, staffing, service area, and population.
6 | Identify responsible positions or partner organizations rather than relying only on the names of current employees. | Identify responsible positions or partner organizations rather than relying only on the names of current employees. | Identify responsible positions or partner organizations rather than relying only on the names of current employees. | Identify responsible positions or partner organizations rather than relying only on the names of current employees.
7 | Use dates or project quarters that fall within the allowable project period and demonstrate a reasonable implementation sequence. | Use dates or project quarters that fall within the allowable project period and demonstrate a reasonable implementation sequence. | Use dates or project quarters that fall within the allowable project period and demonstrate a reasonable implementation sequence. | Use dates or project quarters that fall within the allowable project period and demonstrate a reasonable implementation sequence.
8 | Ensure that every activity is allowable under the RFA and consistent with the project narrative, budget, proposed population, and implementation capacity. | Ensure that every activity is allowable under the RFA and consistent with the project narrative, budget, proposed population, and implementation capacity. | Ensure that every activity is allowable under the RFA and consistent with the project narrative, budget, proposed population, and implementation capacity. | Ensure that every activity is allowable under the RFA and consistent with the project narrative, budget, proposed population, and implementation capacity.
9 | Use performance measures that can be collected and reported without unnecessary burden. Do not propose collection of personally identifiable or protected health information unless specifically authorized and necessary. | Use performance measures that can be collected and reported without unnecessary burden. Do not propose collection of personally identifiable or protected health information unless specifically authorized and necessary. | Use performance measures that can be collected and reported without unnecessary burden. Do not propose collection of personally identifiable or protected health information unless specifically authorized and necessary. | Use performance measures that can be collected and reported without unnecessary burden. Do not propose collection of personally identifiable or protected health information unless specifically authorized and necessary.
10 | Review the completed plan using the quality checklist before submission. | Review the completed plan using the quality checklist before submission. | Review the completed plan using the quality checklist before submission. | Review the completed plan using the quality checklist before submission.
3. How to Develop a Strong SMARTIE Objective | 3. How to Develop a Strong SMART Objective | 3. How to Develop a Strong SMART Objective | 3. How to Develop a Strong SMART Objective | 3. How to Develop a Strong SMART Objective
A project goal describes the broad change the project seeks to advance. A SMARTIE objective describes a specific result that the project expects to achieve within a defined period. | A project goal describes the broad change the project seeks to advance. A SMART objective describes a specific result that the project expects to achieve within a defined period. | A project goal describes the broad change the project seeks to advance. A SMART objective describes a specific result that the project expects to achieve within a defined period. | A project goal describes the broad change the project seeks to advance. A SMART objective describes a specific result that the project expects to achieve within a defined period. | A project goal describes the broad change the project seeks to advance. A SMART objective describes a specific result that the project expects to achieve within a defined period.
SMARTIE Element |  | Question to answer
Specific |  | What population, location, activity, or result is addressed?
Measurable |  | What evidence will show progress or completion?
Achievable |  | Is the result realistic given the proposed resources, staffing, partners, and project period?
Relevant |  | How does the result advance the proposed project and the purpose of the RFA?
Time-bound |  | By what date or project quarter will the result be achieved?
Inclusive |  | How will the populations or communities intended to benefit from the project be meaningfully included in planning, implementation, decision-making, or evaluation?
Equitable |  | How will the result address identified disparities, barriers, or differences in access, resources, opportunities, or outcomes for the populations or communities served?
Objective-writing formula |  | By [date], [responsible organization/project] will [action or result] for [population or setting], achieving [measurable target], as demonstrated by [data source or evidence], while meaningfully including [community/population/partners] in [planning, implementation, decision-making, or evaluation] and using [equitable/culturally responsive strategies] to address [identified barriers, disparities, or differences in access, resources, opportunities, or outcomes].
Example |  | By February 28, 2029, the project will deliver at least 24 population-based prevention workshops to at least 480 youth and caregivers across three participating communities, with at least 80% of responding participants reporting increased knowledge of two or more behavioral-health protective practices or community support resources. Workshops will be informed by youth, caregiver, and community input and delivered using culturally and linguistically responsive approaches that address identified barriers to participation and access.
Needs improvement |  | Stronger objective
Hold wellness workshops for youth. |  | By the end of Project Year 1, deliver 12 wellness workshops to at least 240 youth, with at least 80% of responding participants reporting increased knowledge of two protective practices.
Develop outreach materials. |  | By the end of Quarter 2, finalize and begin using an outreach package informed by input from at least 30 youth, caregivers, and community representatives across all proposed communities.
4. Definitions for Completing the Form | 4. Definitions for Completing the Form | 4. Definitions for Completing the Form | 4. Definitions for Completing the Form | 4. Definitions for Completing the Form
Project goal or strategy addressed |  | The broader project result, strategy, or component supported by the objective.
Major activities |  | The principal actions necessary to achieve the objective. Activities explain what the project will do; they are not the result themselves.
Deliverable |  | A tangible product, completed requirement, or other verifiable evidence of performance, such as a finalized outreach plan, completed training series, or submitted performance summary.
Milestone |  | A significant stage or decision point showing that implementation is progressing, such as completion of recruitment, launch of activities, or execution of a partnership protocol.
Performance measure |  | The variable used to assess progress or results, such as workshops completed, participants reached, percentage reporting increased knowledge, or materials finalized.
Target |  | The expected level of performance, expressed numerically or through another objectively verifiable standard.
Data source/method |  | The records, instruments, or processes used to obtain the performance information, such as activity logs, aggregate attendance records, anonymous surveys, or document review.
5. Implementation Plan Objective Form | 5. Implementation Plan Objective Form | 5. Implementation Plan Objective Form | 5. Implementation Plan Objective Form | 5. Implementation Plan Objective Form
Project goal or strategy addressed |  | Identify the project goal, strategy, or component this objective supports.
SMARTIE objective |  | State one specific, measurable, achievable, relevant, time-bound, inclusive, and equitable result.
Major activities |  | List the principal implementation steps. Do not list routine day-to-day administrative tasks.
Responsible position(s) and partner(s) |  | Identify accountable positions or organizations; do not rely solely on employee names.
Start and completion timeframe |  | Start: ____________________ Anticipated completion: ____________________
Deliverable(s) or milestone(s) |  | Identify tangible evidence that an important stage or result has been completed.
Performance measure(s) and target(s) |  | State what will be measured and the expected numeric or otherwise verifiable level of performance.
Data source and collection method |  | Identify where the information will come from and how it will be collected and reported.
7. Applicant Quality Checklist | 7. Applicant Quality Checklist | 7. Applicant Quality Checklist | 7. Applicant Quality Checklist | 7. Applicant Quality Checklist
Before submitting the application, confirm each item below. | Before submitting the application, confirm each item below. | Before submitting the application, confirm each item below. | Before submitting the application, confirm each item below. | Before submitting the application, confirm each item below.
☐ | The plan covers the full proposed project period. | The plan covers the full proposed project period. | The plan covers the full proposed project period. | The plan covers the full proposed project period.
☐ | Each objective states a meaningful result rather than only an activity. | Each objective states a meaningful result rather than only an activity. | Each objective states a meaningful result rather than only an activity. | Each objective states a meaningful result rather than only an activity.
☐ | Each objective is specific, measurable, achievable, relevant, and time-bound. | Each objective is specific, measurable, achievable, relevant, and time-bound. | Each objective is specific, measurable, achievable, relevant, and time-bound. | Each objective is specific, measurable, achievable, relevant, and time-bound.
☐ | Each objective contains a clear numeric or otherwise verifiable target. | Each objective contains a clear numeric or otherwise verifiable target. | Each objective contains a clear numeric or otherwise verifiable target. | Each objective contains a clear numeric or otherwise verifiable target.
☐ | The major activities are sufficient to accomplish the objective without becoming a weekly task list. | The major activities are sufficient to accomplish the objective without becoming a weekly task list. | The major activities are sufficient to accomplish the objective without becoming a weekly task list. | The major activities are sufficient to accomplish the objective without becoming a weekly task list.
☐ | Every objective identifies responsible positions or organizations. | Every objective identifies responsible positions or organizations. | Every objective identifies responsible positions or organizations. | Every objective identifies responsible positions or organizations.
☐ | The proposed dates are realistic and fall within the allowable project period. | The proposed dates are realistic and fall within the allowable project period. | The proposed dates are realistic and fall within the allowable project period. | The proposed dates are realistic and fall within the allowable project period.
☐ | Deliverables and milestones are distinguishable from performance measures and targets. | Deliverables and milestones are distinguishable from performance measures and targets. | Deliverables and milestones are distinguishable from performance measures and targets. | Deliverables and milestones are distinguishable from performance measures and targets.
☐ | The proposed data sources are available, feasible, and appropriate for quarterly reporting. | The proposed data sources are available, feasible, and appropriate for quarterly reporting. | The proposed data sources are available, feasible, and appropriate for quarterly reporting. | The proposed data sources are available, feasible, and appropriate for quarterly reporting.
☐ | The plan includes both implementation/reach and intended-result objectives. | The plan includes both implementation/reach and intended-result objectives. | The plan includes both implementation/reach and intended-result objectives. | The plan includes both implementation/reach and intended-result objectives.
☐ | The plan is consistent with the application narrative, budget, staffing plan, partnerships, and requested funding. | The plan is consistent with the application narrative, budget, staffing plan, partnerships, and requested funding. | The plan is consistent with the application narrative, budget, staffing plan, partnerships, and requested funding. | The plan is consistent with the application narrative, budget, staffing plan, partnerships, and requested funding.
☐ | All activities are allowable under the RFA and remain within population-based promotion and prevention. | All activities are allowable under the RFA and remain within population-based promotion and prevention. | All activities are allowable under the RFA and remain within population-based promotion and prevention. | All activities are allowable under the RFA and remain within population-based promotion and prevention.
☐ | Targets reflect the applicant’s actual capacity and are not copied from the illustrative example. | Targets reflect the applicant’s actual capacity and are not copied from the illustrative example. | Targets reflect the applicant’s actual capacity and are not copied from the illustrative example. | Targets reflect the applicant’s actual capacity and are not copied from the illustrative example.
8. Quarterly Reporting Alignment | 8. Quarterly Reporting Alignment | 8. Quarterly Reporting Alignment | 8. Quarterly Reporting Alignment | 8. Quarterly Reporting Alignment
For each approved SMARTIE objective, quarterly progress reports will require the subrecipient to describe: | For each approved SMART objective, quarterly progress reports will require the subrecipient to describe: | For each approved SMART objective, quarterly progress reports will require the subrecipient to describe: | For each approved SMART objective, quarterly progress reports will require the subrecipient to describe: | For each approved SMART objective, quarterly progress reports will require the subrecipient to describe:
• | Activities and milestones completed during the quarter; | Activities and milestones completed during the quarter; | Activities and milestones completed during the quarter; | Activities and milestones completed during the quarter;
• | Cumulative progress toward each performance target; | Cumulative progress toward each performance target; | Cumulative progress toward each performance target; | Cumulative progress toward each performance target;
• | Current performance results and supporting data source; | Current performance results and supporting data source; | Current performance results and supporting data source; | Current performance results and supporting data source;
• | Barriers, delays, or material variances from the approved plan; | Barriers, delays, or material variances from the approved plan; | Barriers, delays, or material variances from the approved plan; | Barriers, delays, or material variances from the approved plan;
• | Corrective actions, technical assistance needs, or proposed modifications; and | Corrective actions, technical assistance needs, or proposed modifications; and | Corrective actions, technical assistance needs, or proposed modifications; and | Corrective actions, technical assistance needs, or proposed modifications; and
• | Activities and milestones planned for the next reporting period. | Activities and milestones planned for the next reporting period. | Activities and milestones planned for the next reporting period. | Activities and milestones planned for the next reporting period.

## Implementation Plan
Implementation Plan - Blank Template
Applicant:
Project:
Population/Service Area:
Overall Project Goal:
Objective 1:
SMARTIE Objective
Major Activities
Responsible Position(s)/Partner(s)
Start Date and Completion Date
Deliverable or Milestone
Performance Measure and Target
Data Source/Method
Quarterly Reporting Evidence
Objective 2:
SMARTIE Objective
Major Activities
Responsible Position(s)/Partner(s)
Start Date and Completion Date
Deliverable or Milestone
Performance Measure and Target
Data Source/Method
Quarterly Reporting Evidence
Objective 3:
SMARTIE Objective
Major Activities
Responsible Position(s)/Partner(s)
Start Date and Completion Date
Deliverable or Milestone
Performance Measure and Target
Data Source/Method
Quarterly Reporting Evidence
Objective 4:
SMARTIE Objective
Major Activities
Responsible Position(s)/Partner(s)
Start Date and Completion Date
Deliverable or Milestone
Performance Measure and Target
Data Source/Method
Quarterly Reporting Evidence

## Illustrative Example
Implementation Plan - Illustrative Example
Below is a fictional example of a completed Implementation Plan that demonstrates the expected level of detail required for the completing the blank template. This is an ILLUSTRATIVE EXAMPLE ONLY and does not establish preferred activities, populations, project size, performance levels, or numerical targets. Applicants should develop objectives, activities, measures, and targets appropriate to their proposed project, population, organizational capacity, and requested funding.
Applicant: | Community Wellness Collaborative
Project: | Youth and Family Wellness Initiative
Population/Service Area: | Youth ages 12–18 and their parents/caregivers in three rural communities
Overall Project Goal: | Strengthen protective factors and increase behavioral-health knowledge among youth and caregivers through culturally and linguistically responsive, population-based prevention activities.
Objective 1: Community engagement and project preparation
SMARTIE Objective | By June 30, 2027, the Youth and Family Wellness Initiative will engage at least 30 youth, caregivers, and community representatives, including individuals from populations most impacted by behavioral health disparities, in accessible and culturally and linguistically responsive planning activities. Participant input will be documented and incorporated into the initiative’s finalized outreach and implementation approach to address identified community needs, strengths, and barriers to participation and access.
Major Activities | Conduct three listening sessions—one in each participating community—with youth, caregivers, schools, community organizations, and other relevant partners. Review feedback to identify access, cultural, linguistic, scheduling, and communication considerations. Finalize the outreach strategy, annual activity calendar, and culturally and linguistically responsive participant materials.
Responsible Position(s)/Partner(s) | Project Director; Community Engagement Coordinator; participating school and community-organization representatives
Start Date and Completion Date | March 1–June 30, 2027
Deliverable or Milestone | Final community-engagement summary, outreach strategy, implementation calendar, and participant materials
Performance Measure and Target | At least three listening sessions completed; at least 30 total community participants engaged; all three participating communities represented; final implementation materials document how community feedback was considered and incorporated
Data Source/Method | Listening-session attendance records; participant demographic information collected voluntarily and in aggregate; facilitator notes; feedback summary; final implementation materials
Quarterly Reporting Evidence | Number and type of engagement activities completed; number and characteristics of participants reached; major themes identified; resulting changes to the project’s outreach or implementation approach
Objective 2: Delivery and population reach
SMARTIE Objective | By February 28, 2029, deliver at least 24 population-based behavioral health promotion and prevention workshops to at least 480 youth and caregivers across the three participating communities, with at least 40% of participants representing populations identified in the application as underserved or experiencing barriers to behavioral health information and resources. Workshops will be informed by youth, caregiver, and community input and delivered using accessible, culturally and linguistically responsive approaches designed to address identified barriers to participation, information, and resources.
Major Activities | Adapt workshop materials for the proposed communities while maintaining consistency with the approved project approach. Schedule workshops in accessible community settings and at varied times. Conduct targeted outreach through schools, community organizations, faith communities, and other trusted messengers. Provide language access and reasonable accessibility accommodations as needed. Deliver workshops and monitor participation across communities and population groups.
Responsible Position(s)/Partner(s) | Program Manager; Prevention Educators; Community Engagement Coordinator; participating community partners
Start Date and Completion Date | July 1, 2027–February 28, 2029
Deliverable or Milestone | Completion of 24 workshops and submission of quarterly aggregate participation and activity data
Performance Measure and Target | At least 24 workshops completed; at least 480 total participant contacts; activities offered in all three communities; at least 40% of participants drawn from the underserved populations identified in the approved application
Data Source/Method | Activity logs; aggregate attendance records; voluntary participant demographic information; outreach records; accommodation and language-access logs
Quarterly Reporting Evidence | Workshops planned and completed; participant reach by location and audience; aggregate participant characteristics; outreach methods used; accessibility or language services provided; explanation of progress toward cumulative targets
Objective 3: Participant knowledge and protective factors
SMARTIE Objective | By February 28, 2029, at least 80% of responding workshop participants, including participants from populations identified as underserved or experiencing barriers to behavioral health information and resources, will report increased knowledge of at least two behavioral health protective practices or community support resources immediately following participation in an accessible, culturally and linguistically responsive project workshop informed by youth, caregiver, and community input.
Major Activities | Develop a brief, accessible post-workshop feedback tool. Train facilitators on consistent administration and participant privacy. Collect anonymous participant responses following each workshop. Review aggregate results quarterly and use the findings to identify opportunities to strengthen workshop content, facilitation, outreach, or accessibility.
Responsible Position(s)/Partner(s) | Evaluation and Learning Coordinator; Program Manager; Prevention Educators
Start Date and Completion Date | July 1, 2027–February 28, 2029
Deliverable or Milestone | Quarterly aggregate performance summaries and final project performance summary
Performance Measure and Target | At least 80% of participants who complete the post-workshop feedback tool report increased knowledge of at least two protective practices or community support resources; feedback response rate of at least 70%
Data Source/Method | Anonymous post-workshop feedback tool; workshop attendance totals used to calculate response rates; quarterly aggregate performance summaries
Quarterly Reporting Evidence | Number of participants attending; number and percentage providing feedback; percentage reporting increased knowledge; notable differences by workshop type or location, when data are sufficient; program adjustments made in response to findings
Objective 4: Continuous improvement and sustainability
SMARTIE Objective | By February 28, 2029, complete at least six quarterly continuous-improvement reviews that meaningfully incorporate feedback and outcome data from participating youth, caregivers, community representatives, and populations identified as underserved or experiencing barriers to behavioral health resources, and develop a written continuation strategy identifying at least three feasible and equitable actions for maintaining, adapting, or integrating successful project activities after the CDBHI funding period, with consideration of community priorities, access barriers, and differing population needs.
Major Activities | Review implementation progress, participant reach, performance results, community feedback, and barriers at least quarterly. Document agreed corrective or improvement actions. Consult participating organizations and community representatives regarding activities suitable for continuation or integration into existing programs. Identify potential organizational, partnership, and funding strategies.
Responsible Position(s)/Partner(s) | Project Director; Program Manager; Evaluation and Learning Coordinator; participating partner representatives
Start Date and Completion Date | July 1, 2027–February 28, 2029
Deliverable or Milestone | Six quarterly continuous-improvement summaries and one final continuation strategy
Performance Measure and Target | At least six documented reviews completed; improvement actions assigned and monitored following each review; final strategy identifies at least three feasible continuation actions and the responsible organization or position for pursuing each action
Data Source/Method | Quarterly review agendas and summaries; performance reports; improvement-action tracker; partner consultation records; final continuation strategy
Quarterly Reporting Evidence | Review completed; data considered; implementation challenges identified; decisions or corrective actions adopted; status of prior improvement actions; progress toward the continuation strategy